## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
HomeChef |  | 1month | 2021-08-23 | 2021-09-23 | 2021-09-27
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design | 2021-08-23 |  | 1day
1.1 | Project Defination | 2021-08-24 | 2021-08-26 | 2days
1.2 | Finish webpage | 2021-08-27 | 2021-08-29 | 2days
1.3 | Project Design | 2021-08-30 | 2021-09-04 | 4days
2 | Coding | 2021-09-05
2.1 | Phase 1 | 2021-09-05 | 2021-09-11 | 6days
2.2 | Phase 2 | 2021-09-12 | 2021-09-16 | 4days
2.3 | Additional Features | 2021-09-17 | 2021-09-19 | 2days
3 | Testing | 2021-09-23
3.1 | Phase 1 Testing | 2021-09-23 | 2021-09-24 | 1day
3.2 | Modification /Any changes | 2021-09-24 | 2021-09-24 | 1day
3.3 | Phase 2 Testing | 2021-09-25 | 2021-09-25 | 1day
3.4 | Modification /Any changes | 2021-09-25 | 2021-09-25 | 1day
3.5 | Final Testing | 2021-09-26 | 2021-09-26 | 1day
4 | Documentation | 2021-09-25 |  | 1day
4.1 | User Guide
4.2 | Presentation | 2021-09-26 | 2021-09-26 | 1day

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Backend
| Member Name | Rasika karde
| PRN No | 210543181036
| Description | Backend Work,API Consumption,All DB Related Work
2 | Role | frontend
| Member Name | Kavita Brahmankar
| PRN No | 210543181040
| Description | ReactJS, UI Design, API Connectivity .
3 | Role | Database-queries(restapi)/ppt
| Member Name | Renuka Petkar
| PRN No | 210543181071
| Description | pptpresentation
4 | Role | frontend/Documentation
| Member Name | Archana sapkal
| PRN No | 210543181091
| Description | css,Reactstrap/project Documentation